Talk presented in Eilat						              W. Blum 9.11.99

+ corr.

# MDT Storage and Transport

by W. Blum

Contents:

- First scenario: early delivery – long term storage at CERN

A. 	Time development of the store

B. 	Space requirements

- Second scenario: late delivery – long term storage at home

A.  Time requirements

1. Estimate of handling time after arrival

2. Estimate if the time needed for the tests and recommisioning

3. Time required for mounting MDTs and RPCs together

4. Time required by CERN logistics

5. Total time needed between arrival and installation

B. Space requirements

III.	Material for storage and transport

A.	Frames for the small chambers

B.	Frames for the big chambers

1.	Container sizes and names

2.	How many chambers in one container ?

3.	Containers required for the total production of each centre

IV.	Planning of individual sites

# Appendix 1:	List of Barrel chambers and sizes

Appendix 2:	List of End Cap chambers and sizes

# MDT Storage and Transport

The path of a chamber:

| Operation (a) | Scenario 1 (b) | Scenario 2 (b) |
| --- | --- | --- |
| Glueing T, IS QA/QC, tests (T) Finish (gas, patch p., elx., B-,T-sensors,..) T Long-term storage T, (IS) Tests, recommissioning T, IS Premounting where applicable (RPCs, wheels, ..) (T), IS Transport to underground cavern | H H H H, partly C to C C C C C C C | H H H H H H to C C C C C |

(a)	T = transport, IS = intermediate storage

(b)	H = at home (on or near the production site), C = CERN

For each of the two scenarios we have requirements in space, in time and in equipment for storage and transport. These will be discussed in the following. The situation in the first few moths of the coming year will be seperately addressed.

# I. First Scenario: early delivery - long time storage at CERN

•	Chambers are shipped to CERN soon after assembly

•	Final appliances (B-field sensors, alignment pieces, FE electronics, and other material not available in the beginning of production) are done at CERN

•	One type of test will probably happen immediately after arrival at CERN, another type of test just before installation, several years later.

•	Teams from the institutes would have to travel to CERN in order to finish and test their chambers. No help from CERN.

•	Any storage at CERN would have to use the height of the hall, chambers would be stacked to 6 or 8 m. For frames see further down.

•	Work on the chambers is easy if access to chambers is only needed at the chamber ends  –  the frames allow this access without removing the chambers.

•	If, in order to complete the production of their chambers at CERN, teams need to get at the chamber from the other sides they have to remove the chambers to a working area using special tools for handling the chambers. CERN will probably provide the space needed for this if requested; teams would probably share such working areas.  – This solution is very expensive on resources; not many institutes have opted for it. CERN does not favour it.

# A.   Time development of the store

the store would be continuously filled by regular transports that arrive during the 3 years of production. The store would be emptied within approximately 4 months as discussed below.

# B.   Space requirements

If all chambers are here simultaneously, assuming they are stored in frames 6 to 8 m high, a professional storage area must have a surface of 2000 to 2500 m2, depending on the density of the store, but 6 to 8 m high in any case.

In principle such space would be allocatable in the North Area of CERN. The PE-Division, however, is short of hall space and has put a very low priority on such a passive store. The PE-Division strongly favours the second scenario.

# II. Second scenario: late delivery – long term storage at home

•	MDT chambers come to CERN fully equipped und finished

•	they undergo acceptance tests and recommisioning before installation

•	a fraction of MDT chambers are mounted together with RPCs to form installation units, some others are premounted on frames to go on the large wheels

•	the storage time, and storage space requirements are minimal, only 'intermediate storage' between arrival and installation required

# A.   Time requirements

1. Estimate of handling time after arrival

There is a limit on the handling speed that can be accomplished at CERN upon arrival of chambers. If one half of all chambers, i.e. 600, would have to be unpacked from their shipment containers or wooden boxes into preliminary storage, one single crane  and two busy teams are probably limited at 8 to 16 chambers a day. It would take altogether 7 to 15 weeks.  (This is much better for those chambers where the transport frames are identical to the frames of the intermediate storage). Any waiting time as well as the handling of the remaining half is in addition. Say 4 weeks for that, if it has to happen under the same crane.

For an individual group of 100 chambers from one production centre, the time is estimated to be 6 to 12 days for unpacking and transfer into the container skeletons, provided that they do not have to wait for the crane.

- Estimate of time needed for the tests and the recommissioning:

Example of a production centre that has to deliver 100 chambers. The chambers are accessible from their ends. If one quarter of the chambers take 1/2 day per chamber, one quarter 1/4 day, and the remaining half can be done at 6 per day, they need 6 working weeks for this (0.33 days per chamber). It is also assumed that all teams work in parallel and that they have access to 3 repair tables where they can take a closer look at 3% of their chambers (2 days each for these chambers). –  The mode of operation to do the tests actually has to be debated. There is also a more central model where one team does all the testing. In this case there are more stringent requirements on the speed of testing.

- Time required for mounting the RPCs and the MDTs together

The BMS, BML and BOL chambers will be mounted together with RPCs to form installation units. The CERN team thinks that 8 units should be mounted per day. My own, more careful, view is to also consider a much smaller speed: 3 per day. Therefore I present a range for the time required for the mounting of RPCs.The container skeletons (see below) have to be adjusted to receive the combined parcels.

| Production site | Number of chambers | Type of chambers | Time for mounting RPCs |
| --- | --- | --- | --- |
| Dubna | 72+12 | BMS+BMF | 9 to 28 days |
| Frascati | 96 | BML | 12 to 32 days |
| NIKHEF | 96 | BOL | 12 to 32 days |

4.  Time required by administration and logistics at CERN

Customs formalities seem to be such that  4 containers can be handled 'on a normal half-day'. What this means in reality when material for LHC experiments is coming in at a high rate remains to be seen. I do not expect the Customs office to be a long term bottle neck for us. A special group at CERN, attached to the new SPL Division, is responsible for following all the rules for the introduction of material from outside institutes into CERN. They will be helpful but not extremely fast. We have started to cooperate with the Transport and Logistics Group attached to the ST Division for advice and planning.

- Total time needed between arrival and installation

The above elements are difficult to know precisely to-day. If it turns out that the work to mount the MDTs and the RPCs together does not run as fast as foreseenm it could  partly be done in parallel to the testing.  This will be worked out further. For the moment I present a planning based on 4 months, by which the chambers have to arrive at CERN prior to installation. The installation times as foreseen by the Technical Coordination are depicted in the diagram; they include an estimate for the premouting of the EO-chambers on the frames to go on the big wheels.

# B. Space requirements

It can be seen in the diagram that roughly one half of the chambers would be simultaneously on the CERN site if all chambers would arrive as late as 4 months before their installation. This does not imply that only one half of the storage area of Scenario 1 is needed, because that was based on a very dense passive store. The operations in the 4 months prior to installation also require some extra manoeuvering and working space. For example it would be an advantage to rearrange the endcap chambers in their container skeletons such that they arrive underground in the proper sequence for convenient installation. The required floor space will be roughly 2000 m2 for the MDTs including all manoeuvering and working areas; to be later worked out more precisely.

In this scenario, we can profit from the area allocated to the ATLAS barrel toroid. The toroid parts will be underground, and a good part of the area in the West Hall will be vacated just in time for the MDT chambers to arrive, 4 or 5 months ahead of installation. The floor size will be just right.

# III. Material for storage and transport

The MDT chambers vary in length between 1 and 6.5 m. For this reason the means for storage and transport will not be the same throughout. The following diagram shows the distribution in length of the barrel chambers. They fall into two categories, small and large ones.

# A. Frames for the small chambers

The Rome 3 group has shown a technical solution for the small ones, documented under http://www.roma3.infn.it/atlas/trasporti/trasporti.html. Chambers lie horizontally on foam in individual frames, every chamber is accompanied by its surrounding frame from the glueing table to the underground cavern; a cart can be mounted below for local transport. The frames are stackable to the height of 6 m. 250 MDT chambers are well suited for these frames.

# B. Frames for the big chambers

For the big chambers, standardized 'sea containers' are proposed in the form without roof and without the 4 side walls, 'container skeletons'. The chambers would hang vertically, with the tubes horizontal, in fixtures mounted to the container frames; chambers are supported on the extremeties of the long beams, they rest on rubber or spring elements for shock protection during transport. These fixtures are presently being designed.

Chambers arriving at CERN would always be placed into these frames, which are the principal units to be transported or stored (long term or intermediate). Chamber testing/recommissioning will also take place in these frames. The frames must also be able to house the combined packages of MDT plus RPCs after they have been screwed together. The fixtures under design have to provide for a multiple use of the skeletons.

I. Container sizes and names

|  | Height (ft, mm) Outside ¦ Inside nominal ¦ minimal | Width (ft, mm) Outside ¦ Inside nominal ¦ minimal | Length (ft, mm) Outside ¦ Inside nominal ¦ minimal |
| --- | --- | --- | --- |
| 1A | 8 ft ¦ 2 197 | 8 ft ¦ 2 330 | 40 ft ¦ 11 998 |
| 1B | 8 ft ¦ 2 197 | 8 ft ¦ 2 330 | 30 ft ¦ 8 931 |
| 1C | 8 ft ¦ 2 197 | 8 ft ¦ 2 330 | 20 ft ¦ 5 867 |
| 1D | 8 ft ¦ 2 197 | 8 ft ¦ 2 330 | 10 ft ¦ 2 802 |
| 1AA | 8 ft 6 in ¦ 2 350 | 8 ft ¦ 2 330 | 40 ft ¦ 11 998 |
| 1BB | 8 ft 6 in ¦ 2 350 | 8 ft ¦ 2 330 | 30 ft ¦ 8 931 |
| 1CC | 8 ft 6 in ¦ 2 350 | 8 ft ¦ 2 330 | 20 ft ¦ 5 867 |

2. How many chambers in one container?

Chambers with a width (approx. = tube length) above 5700 mm go into 30-ft containers (type 1B). Chambers with a length (approx. = number of tubes in one layer x 3 cm), also called radial extension, beyond 2050 mm go into containers 8 ft 6 in. high (type 1CC). The rest go into type 1C.

Short chambers with a width below 2600 mm occupy only half the length of a container, very short chambers with a width below 1500 mm take only one third.

The chamber thickness determines the number that fit into a container in the other horizontal direction. The universal width of all containers is 2330 mm minimum.

| Chamber thickness (mm) | Nb. n of chambers | n+1 airgaps, each (mm) |
| --- | --- | --- |
| 168 | 10 | 59 |
| 315 | 6 | 60 |
| 364 | 5 | 85 |
| 367 | 5 | 82 |
| 416 | 5 | 42 |
| 511 | 4 | 57 |

3. Containers required for the total

production of each centre:

| Production centre | Nb. | Type |
| --- | --- | --- |
| Dubna | 2 15 | 1CC 1C |
| Frascati | 24 | 1C |
| Munich | 15 3 | 1CC 1C |
| Freiburg BOF (?) BOG | 2 2 3 | 1CC 1C 1C |
| NIKHEF | 16 8 | 1CC 1C |
| Boston | 12 | 1C |
| Michigan | 4 12 | 1B 1C |
| Seattle | 18 | 1C |
| Protvino | 7 29 | 1B 1C |

Some of these containers may be used twice, for two intermediate storage operations, depending on the the method of delivery (early or late) and of transport (whether the storage containers are also used for transport).

For work to be performed on the chamber ends, the very dense packing of chambers shorter than 2600 mm may be impractical. To be reviewed after some experience.

Some institutes plan to use the container skeletons also for their transport to CERN  (skeletons covered by canvas), and perhaps for short or long storage at home. This is also an economic question. While formal offers will be obtained next year I expect the average cost for the large chambers to be well below 1000 CHF/chamber and less for the ones of intermediate size.

# IV. Planning of individual sites (a)

| Production site (chambs) nb. | Work in CERN store | Provisio | Transport | Store |
| --- | --- | --- | --- | --- |
| NIKHEF (BOL) 96 | Only the tests, can store 50 of their 96 BOL chambers | Are willing to adopt a common scheme | Will presumably adopt container solution | Same container |
| Freiburg 36 (BOF, BOG, BOH) | Everything after 2001 | Under study | Rome scheme | Same frames |
| Munich (BOS, BOF) 88 | Only the tests | Decided | Container scheme | Same container |
| Pavia-Rome (BIL, BIR) 122 | Everything after production | Decided | Rome scheme | Same frames |
| Frascati (BML) 96 | Cannot answer - need more info |  |  |  |
| Thessaloniki (BIS) 128 | Only the tests | Need to find storage till 2001 | Rome scheme | Same frames |
| Dubna (BMS, BMF) 84 | Will try to do just tests |  | If containers, will make own (cost) |  |
| Protvino (EOS, EOL) 192 | Only the tests | Enough space available | Horizontal in wood-en boxes in foam | Same frames |
| Ann Arbor (EMS5, EML3,4,5 EEL2) 80 | 'everything at CERN' but under discussion in US | They do not have any storage at home request tube store | Horizontal, in foam in transport containers | Wood boxes |
| Boston Consortium (EES1, EIS1,2, EIL1,2,3, EMS1,2, EML1) 144 | Only the tests | Enough space available | Horizontal, in foam drawers to be constructed | Crate to be con-structed |
| Seattle 96 (EIL4, EEL1,EES2 EML2, EMS3,4) | Only the tests | Are presently looking to rent space | Horizontal, in air cond'd containers, under discussion | Wood boxes |
| Beijing (BEE) 32 |  |  | Presumably individually by air |  |

(a) Answers received prior to the Eilat meeting and collected on the meeting

# Appendix 1

# Barrel chambers

| Type chamber 1 | Width 2(b) | Length 3(a) | Thick ness 4 | Dist. axes 5 | Max. width 6(c) | Prod. Site 7 | Mass 8 | Chbs 9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | mm | mm | mm | mm | mm |  | kg | nb |
| BIS 1 • | 1000 | 740 | 138 | 1300 | 1325 | Thess | 25 | 16 |
| BIS 2 • | 1820 | 920 | 284 | 1300 | 1820 | Thess | 75 | 80 |
| BIS 3 • | 1820 | 1100 | 284 | 1300 | 1820 | Thess | 105 | 32 |
| sum site |  |  |  |  |  |  |  | 128 |
| BEE * | 1060 | 1460 | 168 | 1154 | 1179 | Beijing | 50 | 32 |
| sum site |  |  |  |  |  |  |  | 32 |
| BIL 1 • | 2820 | 920 | 416 | 2770 | 2820 | Rome/Pav | 160 | 14 |
| BIL 2 • | 1685 | 920 | 416 | 1650 | 1685 | Rome/Pav | 115 | 4 |
| BIL 3 • | 2820 | 1100 | 416 | 2770 | 2820 | Rome/Pav | 180 | 58 |
| BIL 4 • | 1685 | 1100 | 416 | 1650 | 1685 | Rome/Pav | 135 | 20 |
| BIR 1 • | 1685 | 740 | 416 | 1650 | 1685 | Rome/Pav | 100 | 4 |
| BIR 2 • | 1685 | 920 | 416 | 1650 | 1685 | Rome/Pav | 115 | 12 |
| BIR 3 • | 1685 | 1100 | 416 | 1219 | 1685 | Rome/Pav | 135 | 10 |
| sum site |  |  |  |  |  |  |  | 122 |
| BMS 1 | 3220 | 980 | 364 | 3187 | 3220 | Dubna | 155 | 12 |
| BMS 2 | 3220 | 1460 | 364 | 3187 | 3220 | Dubna | 210 | 36 |
| BMS 3 | 3220 | 1700 | 364 | 3187 | 3220 | Dubna | 230 | 24 |
| BMF 1 | 3220 | 1460 | 364 | 3187 | 3220 | Dubna | 210 | 4 |
| BMF 2 | 3220 | 2060 | 364 | 3187 | 3220 | Dubna | 275 | 4 |
| BMF 3 | 3220 | 2180 | 364 | 3187 | 3220 | Dubna | 290 | 4 |
| sum site |  |  |  |  |  |  |  | 84 |
| BML 1 | 3700 | 1220 | 511 | 3667 | 3700 | Frascati | 230 | 32 |
| BML 2 | 3700 | 1460 | 511 | 3667 | 3700 | Frascati | 230 | 16 |
| BML 3 | 3700 | 1700 | 511 | 3667 | 3700 | Frascati | 255 | 48 |
| sum site |  |  |  |  |  |  |  | 96 |
| BOS 1 | 3920 | 1940 | 511 | 4010 | 4035 | Munich | 280 | 12 |
| BOS 2 | 3920 | 2180 | 511 | 4010 | 4035 | Munich | 330 | 60 |
| sum site |  |  |  |  |  |  |  | 72 |
| BOF 1 | 3920 | 1460 | 511 | 4010 | 4035 | Freiburg | 235 | 8 |
| BOF 2 | 3920 | 1940 | 511 | 4010 | 4035 | Freiburg | 315 | 4 |
| BOF 3 | 3920 | 2180 | 511 | 4010 | 4035 | Freiburg | 330 | 4 |
| BOG | 2470 | 1220 | 511 | 2517 | 2542 | Freiburg | 155 | 18 |
| BOH • | 1230 | 1220 | 511 | 1260 | 1285 | Freiburg | 110 | 18 |
| sum site |  |  |  |  |  |  |  | 52 |
| BOL 1 | 5110 | 1700 | 511 | 5077 | 5110 | NIKHEF | 325 | 16 |
| BOL 2 | 5110 | 2180 | 511 | 5077 | 5110 | NIKHEF | 395 | 80 |
| sum site |  |  |  |  |  |  |  | 96 |
| sum of barrel |  |  |  |  |  |  |  | 682 |

a.  	Muon TDR, Section 4.2.2.1 plus 20 mm

b.  	Width measured in the direction of the tubes up to the end of the Faraday cage, Parameter book  mdt_layout_N1.xls

c.  	Max. width is the larger of column 2 and (column 5 plus 25 mm), taking into account the     kinematic mounting block

•  Chamber types BIS, BIL, BIR are 'small', all produced in Thessaloniki and Rome/Pavia, would fit well into the Rome chariots (250 chambers). Also the 18 chambers of the BOH type, produced in Freiburg, are small.

*  Chamber type BEE produced in Beijing, also small, transport by air, storage presumably in the Rome frames (32 chambers)

Appendix 2:

# End cap chambers

| Type chamber 1 | Min width 2 | Max width 3 | Radial extens. 4 | Thick- ness 5 | Prod. Site 6 | Mass 7 | Chbs 8 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | mm | mm | mm | mm |  | kg | nb |
| EES 1 | 2163 | 2586 | 1457 | 315 | Boston | 123 | 16 |
| EIS 1 | 1047 | 1416 | 1277 | 367 | Boston | 91 | 16 |
| EIS 2 | 1425 | 1740 | 1096 | 367 | Boston | 91 | 16 |
| EIL 1 | 1470 | 1995 | 1096 | 367 | Boston | 96 | 16 |
| EIL 2 | 2010 | 2535 | 1096 | 367 | Boston | 114 | 16 |
| EIL 3 | 2230 | 2230 | 376 | 367 | Boston | 47 | 16 |
| EMS 1 | 987 | 1551 | 1937 | 364 | Boston | 116 | 16 |
| EMS 2 | 1560 | 2127 | 1937 | 364 | Boston | 147 | 16 |
| EML 1 | 1335 | 2160 | 1697 | 364 | Boston | 122 | 16 |
| Sum site |  |  |  |  |  |  | 144 |
| EMS 5 | 3288 | 3855 | 1937 | 364 | Michigan | 223 | 16 |
| EML 3 | 3135 | 4080 | 1937 | 364 | Michigan | 219 | 16 |
| EML 4 | 4095 | 5040 | 1937 | 364 | Michigan | 261 | 16 |
| EML 5 | 5055 | 6000 | 1937 | 364 | Michigan | 303 | 16 |
| EEL 2 | 3690 | 4395 | 1457 | 315 | Michigan | 178 | 16 |
| Sum site |  |  |  |  |  |  | 80 |
| EIL 4 | 2730 | 3525 | 1637 | 367 | Seattle | 205 183 | 16 |
| EEL 1 | 3090 | 3675 | 1216 | 315 | Seattle | 133 123 | 16 |
| EES 2 | 2595 | 3018 | 1457 | 315 | Seattle | 137 | 16 |
| EML 2 | 2175 | 3120 | 1937 | 364 | Seattle | 177 | 16 |
| EMS 3 | 2136 | 2703 | 1937 | 364 | Seattle | 172 | 16 |
| EMS 4 | 2712 | 3279 | 1937 | 364 | Seattle | 197 | 16 |
| Sum site |  |  |  |  |  |  | 96 |
| EOS 1 | 1398 | 1893 | 1697 | 364 | Protvino | 118 | 16 |
| EOS 2 | 1902 | 2397 | 1697 | 364 | Protvino | 137 | 16 |
| EOS 3 | 2406 | 2901 | 1697 | 364 | Protvino | 157 | 16 |
| EOS 4 | 2910 | 3333 | 1457 | 364 | Protvino | 153 | 16 |
| EOS 5 | 3342 | 3765 | 1457 | 364 | Protvino | 167 | 16 |
| EOS 6 | 3774 | 4197 | 1457 | 364 | Protvino | 182 | 16 |
| EOL 1 | 1830 | 2655 | 1697 | 364 | Protvino | 141 | 16 |
| EOL 2 | 2790 | 3615 | 1697 | 364 | Protvino | 178 | 16 |
| EOL 3 | 3630 | 4335 | 1457 | 364 | Protvino | 182 | 16 |
| EOL 4 | 4350 | 5055 | 1457 | 364 | Protvino | 206 | 16 |
| EOL 5 | 5070 | 5775 | 1457 | 364 | Protvino | 231 | 16 |
| EOL 6 | 5790 | 6495 | 1457 | 364 | Protvino | 255 | 16 |
| Sum site |  |  |  |  |  |  | 192 |
| Sum of end cap |  |  |  |  |  |  | 512 |