## Sheet1
Delivery of Modules to Oxford
Totals/barrel (assuming 5% spares to Oxford):
Barrel | #modules
B3 | 403
B6 | 706
B4 | 504
B5 | 605
Total | 2218 |  | This is 85.3% of our planned 2600 starts
Reception test rate at Oxford:
Maximum sustainable rate ~ 80 modules/week
Allow for holidays etc - it will take ~ 30 weeks minimum to test the modules
If this rate is started in mid-March, it will take to end October to test the modules before mounting
So we need to supply Oxford at the rate of 80 modules/week from mid-March
Requirement:
From mid-March, modules received at Oxford at rate of:
|  | Rate |  |  | Completion
From Japan: |  | 30 | per week, | first 100 modules to be suitable for B3, next send all B5/6 modules | end Oct
From Scand: |  | 15 | per week, | first 60 modules to be suitable for B3, next send all B5/6 modules | end Aug
From US |  | 20 | per week, | first 100 modules to be suitable for B3, next send all B5/6 modules | end Sept
UK has already sent ~ 150 modules, will keep up with production rate