vc/15-Sep-03

### Week 38 starting 15 Sept 03

### SM18 Operation SCHEDULE Meeting (Tuesdays)

Schedule for this week :

| BENCH | CURRENT MAGNET | STATUS Today(15/09) | Forward look, & Next Magnet |
| --- | --- | --- | --- |
| TBA1 | 2012 | Under Connection | Cold by Thursday 18th Sept for cold tests |
| TBA2 | 3028 | Cold tests completed | Disconnect on Wed 17th(?) if warm & Bring 2021 |
| TBC1 | 3046 | To disconnect: had 2 Thrml Cycles | New magnet to be brought in; work in a stndby to work in parallel with SSS on C2 |
| TBC2 | SSS1 | Warm | Under first time Connection and associated problems |
| TBE1 | 3043 | Cold | Poor Training so far -needs Extended tests |
| TBE2 | 1031 | Warm since Friday 12th | Disconnect & Bring New 2010 |
| TBF1 | 2025 after F2 done? |  | Prepare For Commissioning AFTER F2 |
| TBF2 | 2025 proposed |  | Prepare For Commissioning FIRST |

[Note:  NEXT MAGNET IN PIPELINE : 2002 ]

- Test Coordinator this week:  Marco MTA Technician on call:  (16-3602) :

- Situation From Cryogenics:  J-P Lamboy or ACR Rep.

- Other General Issues

- Problems from Operation Last week (Stephane + Test Supervisor )

| Date | Problem | Type | Application/soft. | Action/advise |
| --- | --- | --- | --- | --- |
| Tuesday 9_M Tuesday 9_A | TBE 2 : TEMA not responding during SSL at 4.4 K. Sun IAS08 : login problem. Config file power disappeared. | AB/CO | TEMA | Solved. |
| Tuesday 9_A | TBC1: MM Shaft position problem with 1 motor of the TRU | MTM |  | Solved by Ewald. |
| Tuesday 9_A | 3046, 1031: problem to insert file in MTF (step 9) | EDMS | MTF | E-mail sent to EDMS support. Problems of rights for type L and context for SM18 OP not defined (typing error) Solved. |
| Tuesday 9_A | TBE2: I earth big (120mA) | MTM |  | Current depending on the bench. Statistic is needed |
| Tuesday 9_A | TBC: IDCCT not working | SL/PO |  | Solved. Apparently! |
| Tuesday 9_A | TBC1: MM big difference of angles between bwd/fwd rotation in few sectors. Shafts 23/24 | MTM |  | Stephane stopped the measurements: Coordinator informed. Investigation on progress. |
| Tuesday 9_A | TBC1: Funny signal on the coils. | MTM |  | Connector Ap1 B/Ap2 B in the mobile rack inverted. |
| Tuesday 9_A Friday 12 | TBA2 : Anticryostat values not correct. TBE1 the same. | MTM |  | Coefficients not updated. Who has to do this? |
| Wednesday 10_A | TBA2: HV test failed | MTM |  | Current leads warmed with a fun. Then OK |
| Wednesday 10_A | TBA2: Cryo lost | MTM/ACR |  | Bad contact in RVLB8 |
| Wednesday 10_A | Plateau of current at 12850 A (ultimate) Extension of the file is .u and not .a | MTM |  |  |
| Wednesday 10_A | TBA2: Minimum energy at 11850 A cannot be triggered. Quench at 1 A! during the manipulation in Vbus ext. | MTM |  | Equip.support called. Bad configuration in the card of the safety matrix used for the minimum energy) (all LEDs of this card must be off). |
| Friday 12_M | MM TBA2 (load line , LHC cycle): Field polarity error | MTM |  | Equip.support called. One sector was in E-coil And pick up coil in a-coil Error listed in the table. Has to be seen during the positioning of the shaft 1.5 kA. |
| Friday 12_N | TBC1 : IDDCT not working (current reading) | SL/PO |  | Equp.support called. A led was switched off. Panel open and a cable was missing. Solved |
| Friday 12_A | TBE1:PLC error Mag300 K and Mag300 K air | MTM/ACR |  | Cryo staff started to purge the magnet as IAP not done. |
| Saturday 13_A | TBA2: 2 Leds of the quench valve card not glowing. Quench at 1 A! during the manipulation in Vbus ext. | MTM |  | Equip.support called. Card changed. Solved |
| Sunday14_M | TBE1: IAP @ cold T coils OK (shaft not there) Offsets in V-gas_int and V_gas_ext leads | MTM |  | Offsets minimized but errors still there. |
| Sunday 14_M | TBE1: Quench at 1.5 kA (all LF and HF) | MTM |  | Trigger one or two cards? Clarification needed. |
| Sunday 14_M | TBE1: Quench at 1.5 kA in Vbus (repeated two times) | MTM |  | Test coordinator informed. Origin under investigation. Test coordinator gives the OK to continue. |
| Monday 15_A | TBE2: IAP @warm Quench heater charged because training quench in TBE1 | MTM |  | Test coordinator informed. Test can be done later and switch to active/passive. |