Vc/12-Jul-04

### Week29 starting 12 July  04

### SM18 Operation Meeting (Tuesdays)

Bench status  on Monday 12 july  13.00hrs

| TBA1 | MBBR2048 | waiting for shafts removal | 82.5 |
| --- | --- | --- | --- |
| TBA2 | MBAR1135 | ICS 4 Final connection | 297.4 |
| TBB1 | MBAL3183 | PT 12 Warm Up | 301.4 |
| TBB2 | MBAL3154 | Prep 5 Pumping + Cool Down | 291.6 |
| TBC1 | MBBL1118 | Finished Ready to go Final scan | 296.9 |
| TBC2 | SSS024 | PT 6.3 Training 3 | 4.8 |
| TBD1 | SSS020 | Stretched Wire @ cold | 1.9 |
| TBD2 | SSS017 | Prep 5 Pumping + Cool Down | 293.6 |
| TBE1 | MBBL3136 | PTE Min. NRJ 3KA Diode Test | 1.9 |
| TBE2 | MBBL1131 | ICS 6 Disconnect Magnet WP07 | 298.1 |
| TBF1 | MBAL3184 | PT 6.1 Training 1 | 1.89 |
| TBF2 | MBBL1115 | PT 12 Warm Up | 241.5 |

7/12/2004 1:03:54 PM    Temperature data are taken from TBSM18 site

Test Coordinator this week: john miles  ; MTM support on call :  (16-3602).

8 Magnets( 7 dipoles+ 1 SSS)   Disconnected after tests last week    ( Sat Midnight to Sat midnight)

- Situation From Cryogenics:  J-P Lamboy or ACR Rep.

  - SSS work :

Bench status  and tests for now( Monday 12/7at 13.00 hrs)  & next few days :  see Video Display

Back to SM18 homepage ¦ Reset ¦ Refresh Active Magnets page

Magnet TB Arrival Out Shafts WP04 HV CDW1 Res. CDW1 HV CDBP HV CDBP Res. CDPT CDAP HV CDW2 Res. WP07 HV MBBR2048 TBA1 03/07/2004 Tests Sequence MBAR1135 TBA2 11/07/2004 Tests Sequence MBAL3183 TBB1 07/07/2004 Tests Sequence MBAL3154 TBB2 10/07/2004 Tests Sequence MBBL1118 TBC1 07/07/2004 Tests Sequence SSS024 TBC2 07/07/2004 Tests Sequence SSS020 TBD1 25/06/2004 Tests Sequence SSS017 TBD2 02/07/2004 Tests Sequence MBBL3136 TBE1 07/08/2004 Tests Sequence MBBL1131 TBE2 01/07/2004 Tests Sequence MBAL3184 TBF1 08/07/2004 Tests Sequence MBBL1115 TBF2 05/07/2004 Tests Sequence

# Results by Week for PREVIOUS week

## Tests

| Magnets under Test from 04-07-2004 to 10-07-2004 |
| --- |
| - | Bench | Magnet | Shafts | Start Date . | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total |  |  |
| 1 | TBA2 | MBBL1123 |  | 28-06-2004 | 24 h. | 49 h. | 78 h. | 12 h. | 0 h. | 05-07-2004 | 168 hours |  |  |
| 2 | TBB1 | MBBL2077 |  | 26-06-2004 | 57 h. | 24 h. | 117 h. | 19 h. | 35 h. | 07-07-2004 | 264 hours |  |  |
| 3 | TBB2 | MBBR2065 |  | 29-06-2004 | 35 h. | 143 h. | 54 h. | 20 h. | 5 h. | 10-07-2004 | 264 hours |  |  |
| 4 | TBC1 | MBAL1089 |  | 27-06-2004 | 55 h. | 36 h. | 102 h. | 26 h. | 11 h. | 07-07-2004 | 240 hours |  |  |
| 5 | TBC2 | SSS016 |  | 24-06-2004 | 81 h. | 24 h. | 98 h. | 5 h. | 35 h. | 05-07-2004 | 264 hours |  |  |
| 6 | TBE1 | MBBL3182 |  | 29-06-2004 | 24 h. | 68 h. | 81 h. | 13 h. | 12 h. | 08-07-2004 | 216 hours |  |  |
| 7 | TBF1 | MBAL1069 |  | 02-07-2004 | 39 h. | 25 h. | 57 h. | 17 h. | 16 h. | 08-07-2004 | 144 hours |  |  |
| 8 | TBF2 | MBBL1126 |  | 25-06-2004 | 105 h. | 55 h. | 49 h. | 12 h. | 1 h. | 05-07-2004 | 240 hours |  |  |

### Quench Information

| - | Magnet | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | MBBL1123 | 11169 A. (MRB-AP1) | 11934 A. (D1-L) | 12297 A. (D2_L) | 12496 A. (D2_L) | 12496 A. (D2-L,MRB) | 12613 A. (D1-U-CFB) | 12690 A. (CFB-A2) | 12741 A. (MRB-A2) | 11991 A. (D2_L) |  | - | - | - |
| 2 | MBBL2077 | 11376 A. (D2-U-S13) | 11878 A. (D2-U-S01) | 12420 A. (D2-U-S01) | 12807 A. (D1-U-S01) | 12852 A. | - | - | - | - | - | - | - | - |
| 3 | MBBR2065 | 11357 A. (D1_U-S01) | 12486 A. (D1-U-S12) |  | - | - | - | - | - | - | - | - | - | - |
| 4 | MBAL1089 | 12205 A. (D2_L) | 12372 A. (D2_L) |  | - | - | - | - | - | - | - | - | - | - |
| 5 | SSS016 | 11865 A. (QI_12) | 11931 A. (QI-34) | 12201 A. (QE-12) | 12528 A. (QI-12) | 12764 A. (QE-12) | 12851 A. | 12850 A. | - | - | - | - | - | - | - |
| 6 | MBBL3182 | 12319 A. (D2-U) | 12471 A. (D1-L) |  | - | - | - | - | - | - | - | - | - | - |  |
| 7 | MBAL1069 | 11489 A. (D1-L) | 12850 A. | - | - | - | - | - | - | - | - | - | - | - |  |
| 8 | MBBL1126 | 11326 A. (D2-L) | 11459 A. (D2-L) | 11882 A. (D2-L) | 12236 A. (D2-U) | 12441 A. (D2-U) | 12446 A. (D2-L) | 12368 A. (D2-L) | 12541 A. (D1_U) | 12648 A. (D2_U) |  | - | - | - |  |

- General Problems last week :

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday_06_A | TBD1 | Training of SSS20 not possible: TCL_aux_x. fault. | ACR |  | Investigation performed by Richard: Temp. Curr.Leads auxiliary fault. ACR team switched to the spare. |
| Tuesday_06_A | TBC2 | WP014 could not be loaded in MTF | TS/CE | MTF | Mail to EDMS support. |
| Tuesday_06_N | TBC1 | HV test at warm on 1118 failed. | MTM | HV |  |
| Wednesday_07_A | TBA1 | 2048 (repeat magnet): how to generate a report HV ? | MTM | HV | Richard contacted: use the option “second run”. |
| Thursday _08_A | TBB2 | MBBL 3183 : SPA occurred during the plateau at 12000 A (PT8). | ACR? | ? | Richard called: PLC showed no fault : lost of cryo OK? Problem of communication between CTH and PLCSE |
| Friday_09_A | TBF2 | MBBL 1115: Iearth not OK after first training quench. | MTM |  | Test stopped: Investigation by Pierre. Cable used for IAP still conned. |
| Friday_09_A | TBA1 | MBBL 2048: abnormal Tcoil on ap 2: Cold (0 C) in CFB side and warm (50 C) on MRB. | ACR/TS/CE | MTF/CTH | Investigation by Richard and Maryline: Scan OK .Origin not clear: calibration parameters for Tcoil not correct? |
| Friday_09_A | TBA1 | Anti-cryostat scan forgotten for SSS 24, SSS20, SSS017. No good value of regulation Temperature. | MTM |  |  |
| Friday_09_N | TBF2 | TBD1: SPA abort at 5 kA. | ACR? |  | . |
| Friday_09_N | TBB2 | 2065: IAP at warm: signal from Vtaps IAPD2bbr offset not OK | MTM | IAP | ? seen during cold tests? |
| Saturday_10_N | TBA2 | HV test on 1123: connector for test of passive bus bar broken. IAP : AC injection leads coming from the generator are broken | MTM |  | Richard informed : he will take an action Test performed with other leads. |
| Saturday_10_N | TBB2 | IAP @warm: Discharge of LF heaters. Trigger hf has not been generated. | AB/CO | hf | Reset the crate and then OK |
| Saturday_10_N | TBC1 | 1118 magnet: Min NRJ for warm up : Peak voltage on D1_L-U at 114 V. | MTM |  | Quench repeated ? |
| Sunday_11_A | TBA | Water leak on the pipe which feed the rotary switch close to RMA | TCR |  | Richard reported to TCR. Responsible from TCR came but not solved. Always leak present. Richard will re-contact TCR Monday for actions. |
| Sunday_11_A | TBC2 | SSS024: HV test failed because condensation on the dipole current leads. | MTM |  | Richard came, put an air blower and connected the 2X60 Amps. |
| Sunday_11_N | TBC2 | SSS024: 2 Triggers have been received during the powering of CD corrector. Lost of cryo OK during the test | AB/CO-ACR? |  |  |