Vc/8-Feb-05

### Week 6 starting 07 Feb 05

### SM18 Operation Meeting (Tuesdays)

Bench status  on Monday 31 Jan 05 @  2/7/2005 3:24:39 PM

|  | A1 | MBAL2123 | Prep 5 Pumping + Cool Down |  |
| --- | --- | --- | --- | --- |
|  | A2 | MBAR3284 | ICS 1 WP04 HV Test Warm |  |
|  | B1 |  |  |  |
|  | B2 | MBBL1193 | ICS 2 Connect Magnet (ICS) |  |
|  | C1 | MBAR3281 | PT 12 Warm Up |  |
|  | C2 | MBAR3253 | Current Lead Upgrade |  |
|  | D1 | SSS127 | ICS 4 Final connection |  |
|  | D2 | SSS098 | PT 13.1 IAP @ Warm |  |
|  | E1 | MBAR3282 | ICS 5 Traveller Last |  |
|  | E2 | MBBR3215 | ICS 4 Final connection |  |
|  | F1 | MBBR2525 | PT 1 IAP @ cold |  |
|  | F2 | MBAL3104 | Prep 5 Pumping + Cool Down |  |

Coordinator this week: P Pugnat; MTM support on call :   16-3602 .

144  Magnets Tested  ( SSS036 twice)

10  dipoles( 0 with MM & long MM)+ 4  SSS(0  with MM) +  0  SSSS

Disconnected after tests last week ( Sat Midnight to Sat midnight)

( 2123 had busbar quenches; 3278 thermal cycle )

- Situation From Cryogenics:  J-P Lamboy or ACR Rep.

- Situation on Repair :

      - Silver Shoes bench F etc

General Points

Problems   Power Converters Software issue & reset

Silver Shoe repairs gong on still  ( outstanding still on C2, F cluster)

SSS36 had Insulation Issues?

Cryo Level problems so 2123 quenching in busbars & so was disconnected & will come back again on A bench

Power Converters software bug appeared Tues meaning needing reset before every use ( OP complained like hell) no solution till Fri pm via PC routine

Sun aft to Mon morning, there were no MRB prepared magnets ( all 3 already used on Sat ) & so bench had to be kept empty

AOB

## Tests

| Magnets under Test from 30-01-2005 to 05-02-2005 |
| --- |
| - | Bench | Magnet | Shafts | Start Date . | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total |  |  |
| 1 | TBA1 | MBAL1173 |  | 29-01-2005 | 28 h. | 79 h. | 15 h. | 13 h. | 11 h. | 04-02-2005 | 144 hours |  |  |
| 2 | TBA2 | MBAR3278 |  | 28-01-2005 | 35 h. | 29 h. | 66 h. | 18 h. | 0 h. | 03-02-2005 | 144 hours |  |  |
| 3 | TBB1 | SSS056 |  | 24-01-2005 | 43 h. | 8 h. | 19 h. | 8 h. | 17 h. | 31-01-2005 | 168 hours |  |  |
| 4 | TBB2 | MBBR3271 |  | 28-01-2005 | 27 h. | 25 h. | 27 h. | 16 h. | 12 h. | 02-02-2005 | 120 hours |  |  |
| 5 | TBD1 | SSS036 |  | 20-01-2005 | 44 h. | 34 h. | 17 h. | 17 h. | 59 h. | 31-01-2005 | 264 hours |  |  |
| 6 | TBD1 | SSS036 |  | 31-01-2005 | 57 h. | 16 h. | 27 h. | 19 h. | 0 h. | 05-02-2005 | 120 hours |  |  |
| 7 | TBD2 | SSS058 |  | 28-01-2005 | 56 h. | 20 h. | 40 h. | 6 h. | 9 h. | 03-02-2005 | 144 hours |  |  |
| 8 | TBE1 | MBAR3280 |  | 30-01-2005 | 28 h. | 25 h. | 23 h. | 15 h. | 8 h. | 03-02-2005 | 96 hours |  |  |
| 9 | TBE1 | MBBL1145 |  | 24-01-2005 | 101 h. | 54 h. | 20 h. | 16 h. | 10 h. | 30-01-2005 | 144 hours |  |  |
| 10 | TBE2 | MBAL3108 |  | 29-01-2005 | 22 h. | 29 h. | 15 h. | 15 h. | 4 h. | 02-02-2005 | 96 hours |  |  |
| 11 | TBF1 | MBAL2128 |  | 24-01-2005 | 74 h. | 30 h. | 26 h. | 18 h. | 20 h. | 31-01-2005 | 168 hours |  |  |
| 12 | TBF1 | MBAR3283 |  | 31-01-2005 | 26 h. | 22 h. | 33 h. | 14 h. | 8 h. | 04-02-2005 | 96 hours |  |  |
| 13 | TBF2 | MBAL1174 |  | 01-02-2005 | 30 h. | 23 h. | 33 h. | 13 h. | 15 h. | 05-02-2005 | 96 hours |  |  |
| 14 | TBF2 | MBAL2123 |  | 24-01-2005 | 36 h. | 27 h. | 30 h. | 19 h. | 56 h. | 01-02-2005 | 192 hours |  |  |

| - | Magnet | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | MBAL1173 | 12068 A. (D1_U) | 12454.8 A. (D2_U) |  | - | - | - | - | - | - | - | - | - | - |
| 2 | MBAR3278 | 9740 A. (D1_U) | 11736 A. (D2_U-S01) | 11808 A. (D2_U_S01) | 12108 A. (D2-U-S01) | 10813 A. (D1-U) | 7197.4 A. (D1-U-S02) | 12401.3 A. (D2_U/S01) | 12724 A. (D2_U_S01) | 12850 A. | - | - | - | - |
| 3 | SSS056 | 12612.6 A. (QI_12) | 0 A. (No Data) |  | - | - | - | - | - | - | - | - | - | - |
| 4 | MBBR3271 | 11263.7 A. (D2-U) | 12426 A. (D1- U) |  | - | - | - | - | - | - | - | - | - | - |
| 5 | SSS036 |  | - | - | - | - | - | - | - | - | - | - | - | - |
| 6 | SSS036 |  | - | - | - | - | - | - | - | - | - | - | - | - |
| 7 | SSS058 | 11860 A. (QE_34) | 12125.3 A. (QE-34) |  | - | - | - | - | - | - | - | - | - | - |
| 8 | MBAR3280 | 11542.5 A. (D2-U) | 12655 A. (D2_L) |  | - | - | - | - | - | - | - | - | - | - |
| 9 | MBBL1145 | 11985.5 A. (D1_U) | 12300.1 A. (D1-L) |  | - | - | - | - | - | - | - | - | - | - |
| 10 | MBAL3108 | 11162 A. (D1-U) | 12685 A. (D2_U) |  | - | - | - | - | - | - | - | - | - | - |
| 11 | MBAL2128 | 11108 A. (D1_L) | 12850 A. (D1-U) |  | - | - | - | - | - | - | - | - | - | - |
| 12 | MBAR3283 | 8920.1 A. (D2-L) | 9136 A. (No Data) | 11010.6 A. (D2_L) | 12322 A. (D2_U) | 12809 A. (D2-L) | 12850 A. | - | - | - | - | - | - | - |
| 13 | MBAL1174 | 11927 A. (D1-U) | 12746 A. (D2_L) |  | - | - | - | - | - | - | - | - | - | - |
| 14 | MBAL2123 | 6245.7 A. (Vbus-Int) | 6185.3 A. (Vbus-Int) | 6110.6 A. (Vbus-Int) |  | - | - | - | - | - | - | - | - | - |

| From 30-01-2005 to 05-02-2005 |
| --- |
| - | Bench | Magnet Name | shafts | Start Date . | Connect Time | Wait +Cooling | Cold Tests | Wait +Warming | Disconnect Time | End Date . | Total | Q |
| 1 | TBF2 | MBAL1174 | False | 01-02-2005 | 30 h. | 23 h. | 33 h. | 13 h. | 15 h. | 05-02-2005 | 4 days | 2 |
| 2 | TBF2 | MBAL2123 | False | 24-01-2005 | 36 h. | 27 h. | 30 h. | 19 h. | 56 h. | 01-02-2005 | 8 days | 3 |
| 3 | TBF1 | MBAL2128 | False | 24-01-2005 | 74 h. | 30 h. | 26 h. | 18 h. | 20 h. | 31-01-2005 | 7 days | 2 |
| 4 | TBF1 | MBAR3283 | False | 31-01-2005 | 26 h. | 22 h. | 33 h. | 14 h. | 8 h. | 04-02-2005 | 4 days | 5 |
| 5 | TBE2 | MBAL3108 | False | 29-01-2005 | 22 h. | 29 h. | 15 h. | 15 h. | 4 h. | 02-02-2005 | 4 days | 2 |
| 6 | TBE1 | MBAR3280 | False | 30-01-2005 | 28 h. | 25 h. | 23 h. | 15 h. | 8 h. | 03-02-2005 | 4 days | 2 |
| 7 | TBE1 | MBBL1145 | False | 24-01-2005 | 101 h. | 54 h. | 20 h. | 16 h. | 10 h. | 30-01-2005 | 6 days | 2 |
| 8 | TBD2 | SSS058 | False | 28-01-2005 | 56 h. | 20 h. | 40 h. | 6 h. | 9 h. | 03-02-2005 | 6 days | 2 |
| 9 | TBD1 | SSS036 | False | 20-01-2005 | 44 h. | 34 h. | 17 h. | 17 h. | 59 h. | 31-01-2005 | 11 days | 0 |
| 10 | TBD1 | SSS036 | False | 31-01-2005 | 57 h. | 16 h. | 27 h. | 19 h. | 0 h. | 05-02-2005 | 5 days | 0 |
| 11 | TBB2 | MBBR3271 | False | 28-01-2005 | 27 h. | 25 h. | 27 h. | 16 h. | 12 h. | 02-02-2005 | 5 days | 2 |
| 12 | TBB1 | SSS056 | False | 24-01-2005 | 43 h. | 8 h. | 19 h. | 8 h. | 17 h. | 31-01-2005 | 7 days | 2 |
| 13 | TBA2 | MBAR3278 | True | 28-01-2005 | 35 h. | 29 h. | 66 h. | 18 h. | 0 h. | 03-02-2005 | 6 days | 8 |
| 14 | TBA1 | MBAL1173 | False | 29-01-2005 | 28 h. | 79 h. | 15 h. | 13 h. | 11 h. | 04-02-2005 | 6 days | 2 |

### Week 30Jan05 to 5 Feb 05

Silver Shoe repairs gong on still  ( outstanding still on C2, F cluster)

SSS36 had Insulation Issues?

Cryo Level problems so 2123 quenching in busbars & so was disconnected & will come back again on A bench

Power Converters software bug appeared Tues meaning needing reset before every use ( OP complained like hell) no solution till Fri pm via PC routine

Sun aft to Mon morning, there were no MRB prepared magnets ( all 3 already used on Sat ) & so bench had to be kept empty

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday _01_M | TBA2 | Noisy signal current during PTE | AB/PO |  | Consequence of the software change. Giorgio contacted Q.King. He advised to perform a reset on RMA (each time befor a 3 kA?) How do we do this? Ne wfacilyti installed on the PCLHC754006\46 next to cluster "C" console. |
| Tuesday _01_M | TBF2 | Hf,lf DAQ problem | AB/CO | Hf,lf | Salem informed A.Raimondo Problem in CPU card swapped from TBC to TBF. |
| Tuesday _01_A | TBF2 | SSS058; Cannot power the EF circuit in TBF. | MTM |  | Investigation by Giorgio. Problem in the clamp. NC opened. |
| Tuesday _01_N | TBD2 | Cryo problem: cool down to 1.9 K stopped. | ACR |  | I |
| Tuesday _01_N | TBD1 | IAP@warm: PLCSE fault not possible to reset | MTM |  |  |
| Tuesday _01_N Wednesday _02_M | TBA2 | SPA abort during LHC cycle Again during training quench. | ? |  | Everything OK. |
| Wednesday _02_A | TBF1 | IDCCT not connected: no recording of the current for LF QH test. | MTM |  | Reconnected and test repeated |
| Thursday _03_M | TBF1 | Quench in Vbus int at 9 kA. | MTM/ACR |  | Electronic checked by Giorgio. OK. Test repeated but He Liq level in the current leads of 75% (60% is enough normally).Training quench performed. |
| Thursday _03_A | TBD1 | Cooling down below 5 K difficult. He level problem? | ACR |  | 2 h of stop |
| Thursday _03_A | TBC1 | IAP test @ warm. Files missing : unable to launch the tests. Retry: application hung. | AB/CO | IAP | Adrian contacted. He solved the problem |
| Thursday _03_A | TBF1 | Hf DAQ did not rearm itself. After a training quench. | AB/CO | hf | Salem contacted Adrian. |
| Thursday _03_N | TBF2 | IAP @ warm: permanent triggers on Vbus Vsupra cards | MTM |  | VT2 and VT2_5 opened. Salem by passed the 2 Taps in the crates |
| Friday _04_M | TBF2 | Alarm on QH2: TminV<500 ms. | MTM | AQA | Salem called. Asked to repeat. Same He advised to proceed. |
| Friday _04_M | TBD2 | HV test @warm failed | MTM |  | Salem and Andre investigated. Performed with the switch in the non correct position. |
| Friday _04_M | TBA2 | Compressor stopped | ACR |  | 2h of stops. |
| Saturday_05_M | TBE1 | Wrong name (3245 instead of 3282) of the magnet for the HV test | MTM | HV | File corrected manually |
| Saturday_05_N | TBC1 | LF_Web gives a vi error when starting-up. LF and HF status windows do not display anything. | AB-CO | lf | Salem contacted. He will inform Adrian Monday |
| Saturday_05_N | TBD2 | SSS098: IAP at Cold (A.C compensation) amplitude error for QI 12-34,QE12-34,QI-E. Offsets could not be adjusted. Vbus Int and Ext trigger when the source voltage exceeds 2.6V. Quench at 15 A in Vbus int | MTM |  | Salem found the origin : adaptator (for right SSS) to match with the VT configuration was not present. Same origin. |
| Saturday_05_N | TBA2 | IAP at warm (13.1) could not be launched, as triggers are present on 'V supra_ext_Lead and Vclamp_Ext' . | MTM |  | Salem removed a by pass on clamp V_taps for Test on A1. I put it back for A2, then OK |
| Sunday_06_M | TBA1 | Short anticryostat resistance in aperture 2 opened. | MTM |  | Salem checked the T value reading . Can survive with the two others. He authorized to go on. |
| Sunday_06_A | TBD2 | Powering of the CD, EF circuits not possible. | ICS |  | Salem found that the connection is not done in the proper way (inverted). He powered the correctors manually. |
| Monday_07_M | TBF1 | MM1 on 2525 magnet : rotation problem in aperture 2 | AB/CO |  | ICS called mechanic team. |
| Monday_07_M | TBC1 | De-excitation test launched without hf DAQ because it cannot be armed | AB/CO |  | Salem changed the card 3. Test repeated. |