### EV- /Week 43 starting 23 October 06

### SM18 Operation Meeting (Tuesdays) 24 Oct 06

Bench status  on Monday 23-oct-2006 at:

10/23/2006 3:26:46 PM

| 7 | A1 | MBAL2342 | Prep 3 CDW1 HV | 296.88 |
| --- | --- | --- | --- | --- |
| 1 | A2 | MBAR1410 | Slow PA | 1.90 |
| 2 | B1 | SSS512 | PT 13.2 Resist. Meas. | 298.58 |
| 5 | B2 | SSS662 | PT 13.2 Resist. Meas. | 296.88 |
| 8 | C1 |  |  | 295.18 |
| 9 | C2 | SSS352 | PT 14 Magnet MAPS | 296.34 |
| 10 | D1 |  |  | 295.8 |
| 4 | D2 | SSS679 | PT5.4: Powering Corrector EF | 2.35 |
| 12 | E1 | MBBR2325 | ICS 3 Traveller after warm test | 297.24 |
| 3 | E2 | MBAL1382 | PT 12 Warm Up | 290.17 |
| 6 | F1 | MBBR2396 | PT 13.2 Resist. Meas. | 296.88 |
| 11 | F2 | MBBR2397 | Prep 5 Cool Down | 292.76 |

CONFIG :  D 6 - AS 2 -  IRSSS 4 ;

Supervisor:  vittorio ;Eq support :  16-3602

9 Magnet Tests completed ( 7 Magnet Stripped )

5 Dipoles tests	(1380 & 1408 with MM)

3 Arc-SSS  tests (339 Not trained)

1  500-series (518 EF corrector NC…)

0  600-series []

General Points:

Test Cryo Limitation and Probems :

- No Training quench can be carry out between Tuesday A / Wednesday A

- Cryo Limitation Wednesday till Friday (Only 1 by 1 magnet can be power).

Special test :

- 4 Benches D2, A2, F2 With MM, and 520 SSW + Long MM

Situation :

- Situation from Cryogenics:  J-P Lamboy or ACR Rep.

- Situation SSSS  :D1 & D2 issues J Halik

- A.O.B..

# From 10/15/2006 to 10/21/2006

Tests Information

| Magnets under Test from 15-10-2006 to 21-10-2006 |
| --- |
| - | Bench | Magnet | Shafts | Start Date | Connect Time | Cooling Time | Cold Test Time | Warming Time | Disconnect Time | End Date | Total | Signed for |
| 1 | TBA2 | MBBL1380 |  | 12-10-2006 | 50 h. | 27 h. | 40 h. | 14 h. | 19 h. | 18-10-2006 | 150 h. | Stripping |
| 2 | TBB1 | SSS518 |  | 12-10-2006 | 47 h. | 15 h. | 85 h. | 7 h. | 31 h. | 20-10-2006 | 185 h. | Stand By |
| 3 | TBB2 | SSS353 |  | 10-10-2006 | 45 h. | 14 h. | 22 h. | 11 h. | 41 h. | 16-10-2006 | 133 h. | Stripping |
| 4 | TBC1 | SSS278 |  | 14-10-2006 | 34 h. | 19 h. | 39 h. | 6 h. | 23 h. | 19-10-2006 | 121 h. | Stripping |
| 5 | TBC2 | SSS339(3) |  | 05-10-2006 | 110 h. | 15 h. | 72 h. | 8 h. | 62 h. | 16-10-2006 | 267 h. | Stand By |
| 6 | TBE1 | MBBR2389 |  | 11-10-2006 | 42 h. | 21 h. | 18 h. | 19 h. | 11 h. | 16-10-2006 | 111 h. | Stripping |
| 7 | TBE2 | MBBL2357 |  | 11-10-2006 | 29 h. | 25 h. | 23 h. | 14 h. | 33 h. | 16-10-2006 | 124 h. | Stripping |
| 8 | TBF1 | MBBL1409 |  | 12-10-2006 | 38 h. | 27 h. | 29 h. | 17 h. | 13 h. | 17-10-2006 | 124 h. | Stripping |
| 9 | TBF2 | MBBL1408 |  | 13-10-2006 | 60 h. | 40 h. | 66 h. | 15 h. | 11 h. | 21-10-2006 | 192 h. | Stripping |

Quench Information

| - | Magnet | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | MBBL1380 | 12382.5 A. (D2_U) | 12677 A. (D1_L) | 12188 A. (D1_L) |  | - | - | - | - | - | - |
| 2 | SSS518 | 12453.5 A. (QE_12) | 12666.5 A. (QE-12) | 12776.6 A. (QI_34) |  | - | - | - | - | - | - |
| 3 | SSS353 | 12460 A. (QE_34) | 12808 A. (QE-12) | 11995.7 A. (No Data) | 12850 A. | - | - | - | - | - | - |
| 4 | SSS278 | 11743.8 A. (QE_12) | 12048.4 A. (QI_12) | 12326.1 A. (QI_12) |  | - | - | - | - | - | - |
| 5 | SSS339 | 11392.8 A. (QI-34) | 11709 A. (QI-34) | 11774 A. (QE-34) | 11886 A. (QE-34) | 11979.7 A. (QE_34) | 12023.1 A. (QI_34) | 12036.9 A. (QE-34) | 12064.4 A. (QI_12) | 12188.2 A. (QE_12) | 12196.2 A. (QE_34) | 12302.7 A. (QI_12) | 12384 A. (QI 12) | 12427.9 A. (QI_34) | 12457.8 A. (QI_34) | 12504.8 A. (QI_12) |  |
| 6 | MBBR2389 | 10264.2 A. (D2_U) | 11338 A. (D1_U) | 12377.9 A. (D2_L) | 12588.5 A. (D2_L) |  | - | - | - | - | - |  |  |  |  |  |  |
| 7 | MBBL2357 | 10637.6 A. (D2_L) | 11129.6 A. (D2_L) | 11616 A. (D2 - L) | 12401.9 A. (D1 - L) | 12858 A. | - | - | - | - | - |  |  |  |  |  |  |
| 8 | MBBL1409 | 10533.2 A. (D1_L) | 11113.1 A. (D1_L) | 11631.8 A. (D2_L) | 12733.3 A. (D1_U) | 12493.8 A. (D1_U) | 12697.9 A. (D1_U) | 12642.6 A. (D1_U) | 12849 A. | - | - |  |  |  |  |  |  |
| 9 | MBBL1408 | 11058.7 A. (D2_U) | 12180 A. (D2_L) | 12630.7 A. (D1_U) | 12850 A. | - | - | - | - | - | - |  |  |  |  |  |  |

| - | Bench | Magnet Name | shafts | Start Date . | Previous | Up to Lyre Test ICS | Tests MTM Time | Leak Search Time | Cooling Time | IAP Cold Tests Time | Training Cold Tests Time | Warming Time | Final MTM Time | Discon. Time | Next | End Date . | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | TBA2 | MBBL1380 | False | 12-10-2006 | 2 h. | 21 h. | 2 h. | 27 h. | 27 h. | 62 h. | 32 h. | 14 h. | 19 h. | 0 h. | 3 h. | 18-10-2006 | 6 days |  |
| 2 | TBB1 | SSS518 | False | 12-10-2006 | 33 h. | 18 h. | 10 h. | 19 h. | 15 h. | 82 h. | 37 h. | 7 h. | 24 h. | 7 h. | 2 h. | 20-10-2006 | 8 days |  |
| 3 | TBB2 | SSS353 | False | 10-10-2006 | 1 h. | 16 h. | 15 h. | 14 h. | 14 h. | 31 h. | 19 h. | 11 h. | 40 h. | 1 h. | 57 h. | 16-10-2006 | 6 days |  |
| 4 | TBC1 | SSS278 | False | 14-10-2006 | 3 h. | 15 h. | 8 h. | 11 h. | 19 h. | 35 h. | 34 h. | 6 h. | 19 h. | 4 h. | 89 h. | 19-10-2006 | 5 days |  |
| 5 | TBC2 | SSS339 | True | 05-10-2006 | 2 h. | 7 h. | 7 h. | 96 h. | 15 h. | 114 h. | 69 h. | 8 h. | 18 h. | 44 h. | 0 h. | 16-10-2006 | 11 days |  |
| 6 | TBE1 | MBBR2389 | False | 11-10-2006 | 6 h. | 16 h. | 3 h. | 23 h. | 21 h. | 51 h. | 11 h. | 19 h. | 8 h. | 3 h. | 3 h. | 16-10-2006 | 5 days |  |
| 7 | TBE2 | MBBL2357 | False | 11-10-2006 | 8 h. | 6 h. | 2 h. | 21 h. | 25 h. | 52 h. | 17 h. | 14 h. | 29 h. | 4 h. | 15 h. | 16-10-2006 | 5 days |  |
| 8 | TBF1 | MBBL1409 | False | 12-10-2006 | 3 h. | 18 h. | 2 h. | 18 h. | 27 h. | 50 h. | 24 h. | 17 h. | 12 h. | 1 h. | 4 h. | 17-10-2006 | 5 days |  |
| 9 | TBF2 | MBBL1408 | True | 13-10-2006 | 1 h. | 15 h. | 3 h. | 42 h. | 40 h. | 106 h. | 42 h. | 15 h. | 10 h. | 1 h. | 6 h. | 21-10-2006 | 8 days |  |

| Date | Bench | Problem | Type | Application/ soft | Action/advise |
| --- | --- | --- | --- | --- | --- |
| Tuesday_17_M | TBC2 | SSS352: Error in QH discharge (IAP at Warm initial) (H4:Imax=44.2,Rinit=20). Check the results at IAP@warm final. | MTM |  | Richard informed. He said this is due to a slightly higher QH charging voltage. |
| Tuesday_17_N | TBD1 | SSS520 : MM is pending due to error in launching the test (Wrong position). | MTM |  | Giorgio corrected the configuration file remotely & advised to proceed. |
| Tuesday_17_N | TBD1 | SSS520: Error in MM3 in a sector. Waiting for Advice. | MTM |  | Measurements have been checked by Guy. Load-line is OK. |
| Wednesday_18_N | TBD1 | SSS520: MM2 aborted since MMP generated an error. |  |  |  |
| Wednesday_18_N | TBD1 | SSS520: MMP failed again with a message, "CPU Address wrong C0000 during data acquisition" & was aborted. | AB/CO |  | Informed Giorgio. He launched the 10000s machine cycle. |
| Wednesday_18_N | TBB2 | SSS662: Permanent triggers are present during IAP at warm (clamp check). | ICS |  | Informed Giorgio. He suggested asking ICS to redo connection of clamp. |
| Thursday_19_N | TBD1 | SSS520: Standard machine cycle (injection_1000s) ticked as done but not executed | MTM |  | Check by Stéphane. Confusion between inj_10000s and inj_1000s. Stéphane managed to use the existing data |
| Friday_20_M | TBD2 | SSS619: magnet cooled down in the gaseous phase. One heater in the gamelle is not working. | MTM |  | Stéphane asked to warm up the magnet, open it, repair the heater and cool down again. Work executed by Mechanic team and P. Legrand Saturday morning. |
| Friday_20_A | TBF2 | MB1408 : Warm_up quench, Warning on DVT of the poles (V=180 V) | MTM |  | Stéphane checked the quench: OK to proceed.. |
| Friday_20_N | TBD1 | SSS520: Ramp number 9. Ultimate current reached but quench during the plateau after one minute. | MTM |  | Stéphane informed. He asked to repeat the test. If the MQ quenched below ultimate put the magnet in ROBTC. |
| Saturday_21_M | TBA1 | MB2382: Provoked quench at nominal instead training quench. | MTM |  | Stéphane asked to complete the training up to the ultimate. |
| Saturday_21_N | TBA2 | MB1410 : Shaft installation: not moving after 700 mm | MTM |  | Shaft blocked in MM position. No displacement for Q.Loc. |
| Saturday_21_N | All | Water supply problem. No cold test possible. | MTM |  | Salem informed. TCR contacted. Salem came and reset PLC CU unit |
| Saturday_21_N | TBA2 | MB1410: While launching PT1 Part I problem with T_coil (wrong values). | MTM |  | Salem informed. |
| Sunday_22_A | TBA2 | MB1410 : First training quench at 11400 A : alarm on MIITs (37 instead of 36.5) | MTM | AQA | Stéphane informed. Check of QH No problem of protection. Quench 1 and 2 analyzed in detail: bump before the quench which induced AQA in error. Delay for the protection too high (17 ms). Stéphane asked Salem to tune the potaim cards. |
| Sunday_22_A | TBA2 | MB1410: Stéphane checked MM1: positioning not good. | MTM |  | Stéphane informed Salem. MMI re-done in his presence. |