| SCT Barrel Module FDR Document |
| --- |
| SCT Barrel Module: Project Plan |
| Abstract |
| This document outlines the responsibilities and schedule for the SCT Barrel Module Project. |
| Prepared by: J. Carter | Checked by: | Approved by: |
| Distribution List |

Table of Contents

1	Scope of the document	3

2	barrel module clusters	3

3	barrel module component supply	3

4	assembly of components into modules	5

5	assembly of modules on to cylinders	5

6	Schedule and procurement release	6

appendix 1: barrel module schedule

# Scope of the document

This document outlines briefly the SCT plans and responsibilities for:

- The supply of the components making up the SCT barrel modules;

- The assembly of these components into modules;

- Module QA;

- The assembly of modules to cylinders;

- Procurement.

# Barrel Module Clusters

The responsibility for producing the barrel modules for the SCT is devolved to four clusters:

| Cluster | Contact Physicist | Cluster Composition | Number of Modules to be delivered by cluster to the barrel assembly sites1 |
| --- | --- | --- | --- |
| Japan | Y. Unno | Hamamatsu Photonics, Hiroshima, KEK, Kyoto-edu, Okayama, Tsukuba | 606 |
| Scandinavia | R. Brenner | Bergen, Oslo, Uppsala | 404 |
| UK-B | A. Carter | Birmingham, Cambridge, QM, RAL | 549 |
| US | C. Haber | LBL, Santa Cruz | 663 |

1The numbers given for the modules to be delivered by clusters to the barrel assembly sites are estimated as 5% more than the final number of modules assembled on the SCT barrel.

The overall co-ordinators of the barrel module programme are A. Carter and Y. Unno.

# BARREL MODULE COMPONENT SUPPLY

The components of the ATLAS SCT barrel modules are described in SCT-BM-FDR-5.  They are, for each module,:

- 4 single-sided silicon microstrip detectors.

- 1 VHCPG baseboard with epoxy coating and 4 beryllia facings fused onto the structure.

- 1 hybrid consisting of a flex circuit, with passive components and glass pitch-adaptor mounted, glued to two carbon bridges.

- 12 ABCD3T-A readout ASICs.

- Electrically conducting epoxy (Eotite P-102) for gluing the ASICs to the hybrid and making electrical contact to the back of the detectors.

- Structural epoxy (AW106/HV953U) with a boron nitride additive (PT1045) for gluing the detectors and the hybrid onto either side of the baseboard.

The responsibility for providing the fully tested components to each module assembly site is summarised in Table 1.

| Component | Cluster | Responsible for cluster supply | Component Source | Location of SCT QA of component |
| --- | --- | --- | --- | --- |
| Silicon Detectors | Japan&US | Y. Unno | Hamamatsu | Hamamatsu, Hiroshima, KEK, Tsukuba |
|  | Scandinavia | B. Stugu | Hamamatsu, Sintef1 | Bergen |
|  | UK-B | J. Carter | Hamamatsu | Cambridge, RAL |
| VHCPG Baseboard complete with BeO facings | All | A. Carter | Industry and Baseboard assembly facility at CERN | CERN |
| Hybrid | All | Y. Unno | Industry | KEK |
| ASICs | Japan, Scandinavia US | A. Grillo | Atmel | Santa Cruz, CERN |
|  | UK-B | A. Carter | Atmel | RAL |
| Electrically conducting epoxy | All | Y. Unno | Industry | KEK |
| Epoxy with boron nitride additive | All | M. Gibson | Industry | RAL |

1Up to 30% of  the detectors used by the Nordic cluster may be supplied by Sintef, subject to acceptance of the Sintef  Pre-series in 2001.

Table 1: Responsibilities for Module Component Supply

4.	ASSEMBLY OF COMPONENTS INTO MODULES

The barrel modules are assembled from their components and tested within the clusters.  These tasks are described in SCT-BM-FDR-6 and SCT-BM-FDR-7.  For series production, the tasks will be located according to Table 2:

| Cluster | ASICs mounted on hybrids and bonded | Full QA of hybrid+ASIC assembly | Module assembled / bonded | Full thermal and mechanical QA of individual modules | Full electrical QA of individual modules |
| --- | --- | --- | --- | --- | --- |
| Japan | Industry | KEK | Hamamatsu | KEK | KEK |
| Scandinavia | Industry | Oslo | Oslo/Uppsala | Uppsala | Bergen, Oslo, Uppsala |
| UK-B | Birmingham | Birmingham | RAL | RAL | Birmingham, Cambridge, QM, RAL |
| US | Industry | LBL, Santa Cruz | LBL | LBL | LBL, Santa Cruz |

Table 2: Module assembly and test locations during series production

The modules reported at this FDR come from the Japanese, Scandinavian and UK-B clusters, with the industrial steps of Table 2 carried out within the SCT cluster.  The modules have been constructed with the full assembly equipment described in SCT-BM-FDR-6, which is commissioned in all four clusters.  The full qualification of all the assembly sites for series module production will take place between October 2001 and February 2002 (see Appendix 1).

- ASSEMBLY OF MODULES ON TO CYLINDERS

The modules from the Scandinavian, UK-B and US clusters will all be sent to Oxford, where they will be assembled on to three of the four SCT cylinders (barrels 3, 4 and 6).  The modules for barrel 5 are being made in Japan and will be assembled on to barrel 5 at KEK.  The complete and fully tested barrels will be sent individually to CERN.  At CERN they will be re-tested and assembled together into the four barrel structure.  An X-ray survey will be carried

out on the complete four barrel structure.

References to full descriptions of the assembly to cylinders, commissioning and survey processes are given in SCT-BM-FDR-1.

# SCHEDULE and procurement RELEASE

The work plan of the SCT is being developed with the aim of delivering the complete sub-detector on the schedule required by ATLAS.

This requires series barrel module production to start in late 2001, with completion in the first half of 2003.  The current SCT barrel module schedule is shown in Appendix 1.

The requirement for barrel module production to begin in 2001 is also driven by budgetary issues; in particular the cost of retaining trained staff on the project to carry out the module assembly tasks.

The long (and different) lead times of the major module components have required the procurement phases to begin in advance of the barrel module FDR or PRR.  The procurement status is as follows:

- Silicon microstrip detectors; contracts are placed for the total supply and the series release has been authorised (SCT-BM-FDR-5.1).  The delivery of series production is in progress.

- Baseboards; tenders have been sent out for the VHCPG and the BeO facings.  These tenders will be opened in May 2001, just before this FDR.  The approval for placing the Contracts in early June is requested from this FDR.

- Hybrids: tenders are to be sent out immediately following this FDR.

- ASICs: it is planned to release the full series production order in July 2001, following both an ASIC PRR and detailed negotiations with Atmel.  In the meantime, sufficient ASICs are being purchased to support the start of series barrel module production according to the appended schedule.

Full funding is secured from the SCT institutes for the procurement of the barrel module components, for module assembly and for the barrel engineering and assembly.

Appendix 1: Barrel Module Schedule